## WBS
WORK BREAKDOWN STRUCTURE
Project Name |  | Zerhuel Bussiness Networking |  |  |  |  | Project Id |  | SCARFONICTECH-DEVSECOPS-00001
Project Manager |  | Nephi |  |  |  |  | Updated |  | 2019-01-01
Objective |  | Establish an application that would enable E-commerce and networking the entire Philippines Enterprise.
ID | Task |  | Dependencies | Status | Effort Hours | Cost | Start Date | Planned Completion | Actual Completion | Resource
1 | Zerhuel Bussiness Networking
2 | INITIATION AND PLANNING
3 | Develop Project Charter |  |  | Closed | 2 |  | 2018-11-17 | 2018-12-01 | 2019-01-05 | Cocoy
4 | meeting for the requirements and pre-requisites |  |  | Closed | 6 |  | 2019-01-01 | 2019-01-01 | 2019-01-05 | ALL
5 | Plan Scope Management |  |  | Closed | 4 |  | 2019-01-02 | 2019-01-05 | 2019-01-05 | ALL
8 | Cost and Budget Management of the Project |  |  | Open | 0.5 | Still Uncomputed | 2018-11-17 | 2019-02-28 |  | Nephi
9 | PRESTAGING
10 | Research and Study the Required information |  |  | Closed | 36 |  | 2018-11-17 | 2019-01-01 | 2019-01-01 | Cocoy
11 | Create FlowChart |  |  | Closed | 8 |  | 2018-11-17 | 2019-01-01 | 2019-01-01 | Nephi
12 | Infrastructure and Server Canvass |  |  | Open | 8 | To Be Decided | 2018-12-01 | 2019-01-05 |  | ALL
13 | Email Services Provider |  |  | Open | 8 |  | 2019-01-01 | 2019-01-05 |  | Cocoy
14 | Product Item and Inventory |  |  | Closed | 4 |  | 2019-01-01 | 2019-01-05 | 2019-01-01 | Nephi
15 | Policy and Law Abiding |  |  | Open | 4 |  | 2019-01-01 | 2019-02-28 |  | Nephi
16 | Documents and DTI Verifcation |  |  | Closed | 4 |  | 2019-01-01 | 2019-02-28 | 2019-01-01 | Nephi
17 | Software Application Life Cycle |  |  | Closed | 24 |  | 2018-11-17 | 2019-01-01 | 2019-01-01 | Cocoy
18 | Spotify Widget |  |  | Open | 2 |  | 2019-01-01 | 2019-01-25 |  | Nephi
19 | RemCo Payee Supplier |  |  | Closed | 4 |  | 2019-01-01 | 2019-01-01 | 2019-01-01 | Nephi
21 | EXECUTION
22 | HTML UI Desgin (Redesign) |  |  | Closed | 8 |  | 2019-01-01 | 2019-01-05 |  | Cocoy
23 | Insertion of the Current Products |  |  | Open | 4 |  | 2019-01-05 | 2019-01-06 |  | Cocoy
24 | Add,Edit Delete of Carts |  |  | Open | 8 |  | 2019-01-07 | 2019-01-11 |  | Cocoy
25 | Buyer Information Entry |  |  | Open | 8 |  | 2019-01-12 | 2019-01-15 |  | Cocoy
26 | RemCo Choices and Location |  |  | Open | 4 |  | 2019-01-16 | 2019-01-18 |  | Cocoy
27 | RemCo Code Entry |  |  | Open | 4 |  | 2019-01-19 | 2019-01-23 |  | Cocoy
| RemCo Voucher |  |  | Open | 4 |  | 2019-01-24 | 2019-01-27 |  | Cocoy
| Checkout and Save Entries |  |  | Open | 2 |  | 2019-01-28 | 2019-01-28 |  | Cocoy
| Gmail Signon |  |  | Open | 8 |  | 2019-01-29 | 2019-02-02 |  | Cocoy
| Accounts Creation |  |  | Open | 8 |  | 2019-02-02 | 2019-02-08 |  | Cocoy
| Admin Dashboard |  |  | Open | 8 |  | 2019-02-09 | 2019-02-11 |  | Cocoy
| Manual Entry for Input the PTN |  |  | Open | 1 |  | 2019-02-12 | 2019-02-12 |  | Cocoy
| Integration of FormSPree |  |  | Open | 8 |  | 2019-02-13 | 2019-02-19 |  | Cocoy
| Order List Entry with searchable bar and current status |  |  | Open | 2 |  | 2019-02-20 | 2019-02-21 |  | Cocoy
| Archives for Data referrence like LBC |  |  | Open | 2 |  | 2019-02-22 | 2019-02-23 |  | Cocoy
28 | USER ACCEPTANCE
29 | User acceptance test |  |  | Open | 8 |  | 2019-02-24 | 2019-02-28 |  | Nephi
30 | Document submission (Configuration, Diagram, Etc) |  |  | Open | 8 |  | 2019-03-01 | 2019-03-09 |  | Cocoy
31 | USERS TRAINING
32 | Developer Training on Usage and management |  |  | Open | 1 |  | 2019-03-10 | 2019-03-16 |  | Cocoy/Nephi
33 | PROJECT CLOSE OUT
34 | Project Acceptance |  |  | Open | 0.5 |  | 2019-03-16 | 2019-03-23 |  | ALL
35 | Payment and aggreement |  |  | Open | 1 | To Be Decided | 2019-03-16 | 2019-03-31 |  | ALL
PROJECT END
| Legend: |  |  |  | Prepared By |  |  | Reviewed By
| Status | Open
Closed
[5 empty] | Francisco S. Abayon |  |  | Nephi Decayo
[5 empty] | Devloper |  |  | CEO
Note on E6: Options are: Open Closed

## Risk
RISK REGISTER
Project Name |  | Zerhuel Bussiness Networking | [5 empty] | Project Id | SCARFONICTECH-DEVSECOPS-00001
Project Manager |  | Francisco Abayon | [5 empty] | Updated | 2019-01-01
ID | Risk Description | Probability | Impact | Detectability | Importance | Category | Trigger Event/Indicator | Risk Response and Description | Risk Mitigation | Contigency Plan | Owner | Status | Date Entered | Date to Review | https://carlodimaandal.com/how-much-does-a-website-cost-in-the-philippines
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0 | [10 empty] | https://www.freehostia.com/free-cloud-hosting/
11 |  |  |  |  | 0 | [10 empty] | https://www.digitalberg.com/free-ssd-web-hosting-cloud/
12 |  |  |  |  | 0 | [10 empty] | https://vpsie.com/pricing/
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
21 |  |  |  |  | 0
22 |  |  |  |  | 0
23 |  |  |  |  | 0
24 |  |  |  |  | 0
25 |  |  |  |  | 0
LEGEND :
| Probability, Impact & Detectability | 4
3
2
1
| Risk Response and Description | Avoidance
Transference
Mitigation
Acceptance
| Status | Open
Closed
Note on C5: Probability: 4: Highly likely/probable (76%-100%) 3: Likely (51%-75%) 2: Somewhat likely (26%-50%) 1: Unlikely/improbable (0%-25%)
Note on D5: Impact: 4: Critical: Threatens the viability of the business or represents failure of the project 3: Severe: Threatens the achievement of business vision or severely reduces project benefits 2: Moderate: May delay achievement of the vision or reduce project benefits 1: Minimal/minor: No impact on business vision but may increase project costs and timescales
Note on E5: Detectability: 4: Determined after impact has been realized 3: Realized upon trigger event 2: Immediately prior to trigger event; can be mitigated prior to trigger if monitored 1: Determined well in advance of occurrence or trigger event
Note on G5: This is a field you can use to identify risks by categories such as technological, personnel, etc.
Note on H5: Wesly G. Peteros: What act or event initiates either the risk occurrence or precipitates the response strategy?
Note on I5: Options are: Avoidance Transference Mitigation Acceptance Include a description of what actions are taken to implement the response.
Note on K5: Wesly G. Peteros: If the risk becomes a reality, what will you do in response, as a backup, or alternative/ workaround?